## 表紙
プロジェクト名
グループ- (2)
| 作成者 |  | Min Htaw Lon | Phoo Pwint Maung | Khin Myint Myat San | Kaung Zan Thaw | May Thazin
| 作成日 |  | 2022-09-22
最終更新日
| 担当 | Min Htaw Lon | Phoo Pwint Maung | Khin Myint Myat San | Kaung Zan Thaw | May Thazin
| フロント | ● | ● | ● | ● | ●
| 管理 | ● | ● | ●
株式会社 ○○○○

## 更新履歴
更新履歴 |  | プロジェクト名 | 作成日
|  |  | 更新日 | 2022-10-28 13:03
| No | 更新内容 | 名前 | 日付
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## 進捗（タスク）
進捗 | プロジェクト名 | [9 empty] | 作成日
[11 empty] | 更新日 | 2022-10-28 13:03
| No | セブ | タスク | 担当者 | 予定スタート | 予定完了 | 期間 | 実際スタート | 実際完了 | 期間 | 完了％
| 1 |  | 進捗 | All | 2022-09-22 | 2022-10-22 | 30 | 2022-09-22 |  | -44826 | 0%
| 2 |  | フロント流れ | MHL,K MMS | 2022-09-22 | 2022-09-26 | 4 | 2022-09-22 | 2022-09-24 | 2 | 100%
| 3 |  | 管理画面流れ | MHL,K MMS | 2022-09-22 | 2022-09-26 | 4 | 2022-09-22 | 2022-09-27 | 5 | 100%
| 4 |  | 要件定義 | MHL | 2022-09-22 | 2022-09-25 | 3 | 2022-09-22 | 2022-09-28 | 6 | 100%
| 5 |  | 画面一覧 | KMMS | 2022-09-27 | 2022-09-30 | 3 | 2022-09-27 | 2022-09-30 | 3 | 100%
| 6 |  | 機能一覧 | MHL | 2022-09-26 | 2022-09-28 | 2 | 2022-09-26 | 2022-09-30 | 4 | 100%
| 7 |  | フロント 画面設計 |  | 2022-09-27 | 2022-09-30 | 3 | 2022-09-27 | 2022-10-02 | 5 | 100%
|  | 1 | 登録 | MTZ | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 2 | パスワード編集 | KZT | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 3 | ログイン | MTZ | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 4 | 患者ホームページ | PPM | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 5 | ユーザーセッティング | MHL | 2022-09-28 | 2022-09-29 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 6 | ユーザーセッティング編集 | MHL | 2022-09-28 | 2022-09-29 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 7 | 医者ペイジ | MTZ | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
|  | 8 | 予約ペイジ | PPM | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 9 | 予約状況 | KZT | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
|  | 10 | 病院住所 | KZT | 2022-09-27 | 2022-09-28 | 1 | 2022-09-27 | 2022-09-28 | 1 | 100%
|  | 11 | 医療情報ブログ | KZT | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
|  | 12 | 緊急時代 | PPM | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
|  | 13 | 献血 | PPM | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
|  | 14 | ウェブサイト案内 | MTZ | 2022-09-28 | 2022-09-29 | 1 | 2022-09-28 | 2022-09-29 | 1 | 100%
0
0
| 8 |  | 管理画面デザイン | All | 2022-09-28 | 2022-10-02 | 4 | 2022-09-29 | 2022-10-02 | 3 | 100%
|  | 1 | 管理ログイン | KZT | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 2 | 管理ホームページ | KZT | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 3 | 病院住所 | KMMS | 2022-09-30 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 4 | 予約ペイジ | KMMS | 2022-09-30 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 5 | 患者病歴 | PPM | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 6 | 患者病歴（加える） | PPM | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 7 | 入院患者 | PPM | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 8 | 入院患者 （加える） | PPM | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 9 | 入院患者（編集） | PPM | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 10 | デート | MTZ | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 11 | 医者カテゴリ | MTZ | 2022-09-29 | 2022-09-30 | 1 | 2022-09-29 | 2022-09-30 | 1 | 100%
|  | 12 | 医者カテゴリ（編集） | MTZ | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 13 | 薬（加える） | MTZ | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 14 | ホームページ記事（加える） | MTZ | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 15 | ホームページ記事（編集） | MHL | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 16 | ブログ | MHL | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 17 | ブログ（加える） | MHL | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 18 | 緊急時代（加える） | MHL | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 19 | 緊急時代（編集） | MHL | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 20 | 献血 | KZT | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 21 | 献血（編集） | KZT | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
|  | 22 | ウェブサイト案内（編集） | MTZ | 2022-10-01 | 2022-10-02 | 1 | 2022-10-01 | 2022-10-02 | 1 | 100%
[7 empty] | 0 |  |  | 0
| 9 |  | Database |  | 2022-10-04 | 2022-10-06 | 2 | 2022-10-04 | 2022-10-07 | 3 | 100%
|  |  | DB 設計 | KMMS | 2022-10-04 | 2022-10-05 | 1 | 2022-10-04 | 2022-10-05 | 1 | 100%
|  |  | DB 図 | KMMS | 2022-10-05 | 2022-10-06 | 1 | 2022-10-05 | 2022-10-07 | 2 | 100%
100%
| 10 |  | フロントページデザイ |  | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-09 | 3 | 100%
|  |  | 必須コンポーネント (ヘッダー、フッター) | PPM | 2022-10-07 | 2022-10-09 |  | 2022-10-06 | 2022-10-07 | 1 | 100%
|  | 1 | 登録 | KZT | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-07 | 1 | 100%
|  | 2 | パスワード編集 | KZT | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-07 | 1 | 100%
|  | 3 | ログイン | KZT | 2022-10-07 | 2022-10-09 | 2 | 2022-10-07 | 2022-10-08 | 1 | 100%
|  | 4 | 患者ホームページ | PPM | 2022-10-07 | 2022-10-09 | 2 | 2022-10-07 | 2022-10-08 | 1 | 100%
|  | 5 | ユーザーセッティング編集 | KZT | 2022-10-07 | 2022-10-09 | 2 | 2022-10-08 | 2022-10-09 | 1 | 100%
|  | 6 | 医者ペイジ | MHL | 2022-10-07 | 2022-10-09 | 2 | 2022-10-08 | 2022-10-09 | 1 | 100%
|  | 7 | 予約ペイジ | KMMS | 2022-10-07 | 2022-10-09 | 2 | 2022-10-07 | 2022-10-08 | 1 | 100%
|  | 8 | 予約状況 | MHL | 2022-10-07 | 2022-10-09 | 2 | 2022-10-07 | 2022-10-08 | 1 | 100%
|  | 9 | 患者病歴 | MHL | 2022-10-07 | 2022-10-09 | 2 | 2022-10-08 | 2022-10-09 | 1 | 100%
|  | 10 | 病院住所 | MHL | 2022-10-07 | 2022-10-09 | 2 | 2022-10-08 | 2022-10-09 | 1 | 100%
|  | 11 | ブログと最近、はやっている病気 | PPM | 2022-10-07 | 2022-10-09 |  | 2022-10-08 | 2022-10-09 | 1 | 100%
|  | 12 | 緊急時代 | PPM | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-07 | 1 | 100%
|  | 13 | 献血 | PPM | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-07 | 1 | 100%
|  | 14 | ウェブサイト案内 | KMMS | 2022-10-07 | 2022-10-09 | 2 | 2022-10-06 | 2022-10-07 | 1 | 100%
[7 empty] | 0 |  |  | 0 | 100%
| 10 |  | 管理ページデザイ |  | 2022-10-09 | 2022-10-11 | 2 | 2022-10-08 | 2022-10-10 | 2 | 100%
|  | 1 | 管理ログイン | KZT | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 2 | 管理ホームページ | KMMS | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 3 | 病院住所 | KMMS | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 4 | 予約ペイジ | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 5 | 患者病歴 | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 6 | 患者病歴（加える） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 7 | 入院患者 | KMMS | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 8 | 入院患者 （加える） | KMMS | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 9 | 入院患者（編集） | KMMS | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 10 | デート | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 11 | 医者カテゴリ | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 12 | 医者カテゴリ（編集） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 13 | 薬（加える） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 14 | ホームページ記事（加える） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 15 | ホームページ記事（編集） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 16 | ブログ | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 17 | ブログ（加える） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 18 | 緊急時代（加える） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 19 | 緊急時代（編集） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 20 | 献血 | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 21 | 献血（編集） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
|  | 22 | ウェブサイト案内（編集） | MTZ | 2022-10-09 | 2022-10-11 | 2 | 2022-10-09 | 2022-10-10 | 1 | 100%
[7 empty] | 0 |  |  | 0 | 100%
| 11 |  | Development（開発） | KMMS MHL PPM KZT | 2022-10-11 | 2022-10-25 | 14 | 2022-10-11 | 2022-10-25 | 14 | 100%
|  |  | 患者サイド | KMMS MHL PPM KZT | 2022-10-11 | 2022-10-25 | 14 |  |  | 0 | 100%
|  | 1 | 登録 | PPM | 2022-10-16 | 2022-10-18 | 2 |  |  | 0 | 100%
|  | 2 | パスワード編集 | PPM | 2022-10-11 | 2022-10-25 | 14 |  |  | 0 | 100%
|  | 3 | ログイン | PPM | 2022-10-11 | 2022-10-25 | 14 |  |  | 0 | 100%
|  | 4 | 患者ホームページ | MHL KZT |  |  | 0 |  |  | 0 | 100%
|  | 5 | ユーザーセッティング | MHL |  |  | 0 |  |  | 0 | 100%
|  | 6 | ユーザーセッティング編集 | MHL |  |  | 0 |  |  | 0 | 100%
|  | 7 | 医者ペイジ | PPM |  |  | 0 |  |  | 0 | 100%
|  | 8 | 予約ペイジ | MHL |  |  | 0 |  |  | 0 | 100%
|  | 9 | 予約状況 | MHL |  |  | 0 |  |  | 0 | 100%
|  | 10 | 病院住所 | PPM |  |  | 0 |  |  | 0 | 100%
|  | 11 | 医療情報ブログ | PPM |  |  | 0 |  |  | 0 | 100%
|  | 12 | 緊急時代 | PPM | 2022-10-14 | 2022-10-16 | 2 |  |  | 0 | 100%
|  | 13 | 献血 | MHL |  |  | 0 |  |  | 0 | 100%
|  | 14 | ウェブサイト案内 | KMMS |  |  | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
|  |  | 管理サイド | KMMS MHL PPM KZT | 2022-10-11 | 2022-10-25 | 14 |  |  | 0 | 100%
|  | 1 | 管理ログイン | PPM | 2022-10-24 | 2022-10-25 | 1 |  |  | 0 | 100%
|  | 2 | 管理ホームページ | MHL | 2022-10-23 | 2022-10-25 | 2 |  |  | 0 | 100%
|  | 3 | デート | KMMS | 2022-10-19 | 2022-10-21 | 2 |  |  | 0 | 100%
|  | 4 | 予約ペイジ | MHL | 2022-10-21 | 2022-10-23 | 2 |  |  | 0 | 100%
|  | 5 | 医者カテゴリ | PPM | 2022-10-16 | 2022-10-18 | 2 |  |  | 0 | 100%
|  | 6 | 医者カテゴリ（編集） | PPM | 2022-10-16 | 2022-10-18 | 2 |  |  | 0 | 100%
|  | 7 | 患者病歴 | MHL | 2022-10-22 | 2022-10-24 | 2 |  |  | 0 | 100%
|  | 8 | 患者病歴（加える） | MHL | 2022-10-23 | 2022-10-24 | 1 |  |  | 0 | 100%
|  | 9 | 薬（加える） | KZT | 2022-10-19 | 2022-10-20 | 1 |  |  | 0 | 100%
|  | 10 | 入院患者 | KMMS | 2022-10-11 | 2022-10-13 | 2 |  |  | 0 | 100%
|  | 11 | 入院患者 （加える） | KMMS | 2022-10-12 | 2022-10-14 | 2 |  |  | 0 | 100%
|  | 12 | 入院患者（編集） | KMMS | 2022-10-13 | 2022-10-15 | 2 |  |  | 0 | 100%
|  | 13 | ウェブサイト案内（編集） | KMMS | 2022-10-16 | 2022-10-18 | 2 |  |  | 0 | 100%
|  | 14 | 病院住所 | PPM | 2022-10-11 | 2022-10-13 | 2 |  |  | 0 | 100%
|  | 15 | ブログ | PPM | 2022-10-17 | 2022-10-19 | 2 |  |  | 0 | 100%
|  | 16 | ブログ（加える） | PPM | 2022-10-17 | 2022-10-19 | 2 |  |  | 0 | 100%
|  | 17 | ホームページ記事（加える） | MHL |  |  | 0 |  |  | 0 | 100%
|  | 18 | ホームページ記事（編集） | MHL |  |  | 0 |  |  | 0 | 100%
|  | 19 | 緊急時代（加える） | PPM | 2022-10-14 | 2022-10-16 | 2 |  |  | 0 | 100%
|  | 20 | 緊急時代（編集） | PPM | 2022-10-14 | 2022-10-16 | 2 |  |  | 0 | 100%
|  | 21 | 献血 | MHL |  |  | 0 |  |  | 0 | 100%
|  | 22 | 献血（編集） | MHL |  |  | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%
[7 empty] | 0 |  |  | 0 | 100%

## 進捗（人）
進捗 | [32 empty] | 作成日
[33 empty] | 更新日 | 2022-09-22
| No | 担当者 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| 1 | Min Htaw Lon
| 2 | Phoo Pwint Maung
| 3 | Khin Myint Myat San
| 4 | Kaung Zan Thaw
| 5 | May Thazin
| No | 担当者 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 1 | Min Htaw Lon
| 2 | Phoo Pwint Maung
| 3 | Khin Myint Myat San
| 4 | Kaung Zan Thaw
| 5 | May Thazin
Note on D6: Lenovo: 要件定義
Note on E6: Lenovo: フロント流れ 要件定義
Note on F6: Lenovo: フロント流れ 管理画面流れ
Note on G6: Lenovo: 管理画面流れ
Note on H6: Lenovo: 流れ確認する 機能一覧
Note on I6: Lenovo: 機能一覧
Note on J6: Lenovo: 機能一覧
Note on K6: Lenovo: collect data for database
Note on L6: Lenovo: user design recheck
Note on M6: Lenovo: user profile setting collect data for database
Note on N6: Lenovo: admin side 1. blog page 2. add blog page 3. emergency situations user side 1. user profile edit
Note on O6: Lenovo: screen design details 1. blood donation page
Note on P6: Lenovo: database discuss
Note on Q6: Lenovo: finalize design user design components
Note on R6: Lenovo: make design components responsive
Note on S6: Lenovo: user 1. header 2. footer 3.toolkit 4. doctor page
Note on T6: Lenovo: user side 1. booking 2. Patient history 3. hospital location
Note on U6: Lenovo: user responsive check
Note on V6: Lenovo: user responsive admin responsive
Note on W6: Lenovo: user responsive admin resoinsive
Note on X6: Lenovo: user design final edit
Note on Y6: Lenovo:
Note on Z6: Lenovo: admin side -blog
Note on AA6: Lenovo: user side - user profile edit
Note on AB6: Lenovo: blog css error resolve blog page
Note on AC6: Lenovo: user side - user page responsive
Note on AD6: Lenovo: admin side - blog CRUD functions user side - blog display
Note on AE6: Lenovo: user side -blood donation done
Note on AF6: Lenovo: patient side - doctor page design change - booking status
Note on AG6: Lenovo: admin side -booking approved function
Note on D7: Lenovo: デザイン について話し合う
Note on E7: Lenovo: デザイン について話し合う
Note on F7: Lenovo: user UI kit
Note on G7: Lenovo: user UI kit admin UI kit
Note on H7: Lenovo: admin UI kit 流れ確認する
Note on I7: Lenovo: User homepage Appointment form
Note on J7: Lenovo: emergency situation page blood donation page
Note on K7: Lenovo: admin side- inpatient admin side- add inpatient
Note on L7: Lenovo: user design recheck
Note on M7: Lenovo: 1. patient history page 2. add patient history page 3. edit inpatient page
Note on N7: Lenovo: admin side pages modification 1. inpatient 2. add inpatient 3. patient history 4. add patient history 5. edit inpatient
Note on O7: Lenovo: screen design details
Note on P7: Lenovo: database discuss
Note on S7: Lenovo: user 1. header 2. footer 3.toolkit 4. user homepage
Note on T7: Lenovo: admin side components user side 1. user blog 2. emergency 3. blood donation
Note on U7: Lenovo: admin responsive check
Note on V7: Lenovo: user login sign up
Note on W7: Lenovo: user login, sign up
Note on X7: Lenovo: admin side - hospital location (add, edit)
Note on Y7: Lenovo: emergency situations -search add new article
Note on Z7: Lenovo: admin nav bar and link all pages patient login,signup
Note on AA7: Lenovo: patient side - sign-up - email already exists
Note on AB7: Lenovo: input form control edit admin side - doctor.php
Note on AC7: Lenovo: admin side - add article table user side - home page article add
Note on AD7: Lenovo: admin side - doctor page search - doctor speciality search
Note on AE7: Lenovo: date and time show in patient side doctor card design edit sql doctor list
Note on AF7: Lenovo: admin side - email session - doctor search function
Note on AG7: Lenovo: admin side -pagination (doctor, hospital location, blood donation)
Note on D8: Lenovo: フロント流れ
Note on E8: Lenovo: フロント流れ 進捗（タスク）
Note on F8: Lenovo: フロント流れ 管理画面流れ
Note on G8: Lenovo: 管理画面流れ admin UI kit
Note on H8: Lenovo: 流れ確認する design schedule
Note on I8: Lenovo: 画面一覧
Note on J8: Lenovo: 画面一覧
Note on K8: Lenovo: admin design schedule
Note on L8: Lenovo: user design recheck 画面一覧
Note on M8: Lenovo: 画面一覧
Note on N8: Lenovo: hospital location page booking page
Note on O8: Lenovo: screen design details documentation check
Note on P8: Lenovo: database discuss make database table
Note on Q8: Lenovo: database table create database
Note on R8: Lenovo: database diagram add new database information discuss user design coding
Note on S8: Lenovo: discuss user design coding schedule user design coding
Note on T8: Lenovo: make schedule for adminpage design code
Note on AE8: Lenovo: admin side -connect sql doctor and date tables - date page
Note on AF8: Lenovo: admin side - edit date page
Note on AG8: Lenovo: admin side - about us page - connect admin and user side
Note on D9: Lenovo: デザイン について話し合う
Note on E9: Lenovo: デザイン について話し合う
Note on F9: Lenovo: user UI kit
Note on G9: Lenovo: user UI kit admin UI kit
Note on H9: Lenovo: admin UI kit 流れ確認する
Note on I9: Lenovo: forget password hospital location
Note on J9: Lenovo: booking status and history emergency situation
Note on K9: Lenovo: admin sode 1. admin login 2. admin homepage
Note on L9: Lenovo: user design recheck
Note on M9: Lenovo: search design references
Note on N9: Lenovo: first aid kit caroussel image change
Note on O9: Lenovo: screen design details
Note on P9: Lenovo: database discuss
Note on S9: Lenovo: discuss admin design coding 1. user forget password 2. user login 3. user register
Note on T9: Lenovo: admi side 1. admin register 2.admin forget password
Note on U9: Lenovo: user side 1. edit user profile
Note on AB9: Lenovo: database update
Note on AE9: Lenovo: add medicine related data
Note on AF9: Lenovo: user forget password patient home page medicine cards
Note on D10: Lenovo: デザイン について話し合う
Note on E10: Lenovo: デザイン について話し合う
Note on F10: Lenovo: user UI kit
Note on G10: Lenovo: user UI kit admin UI kit
Note on H10: Lenovo: admin UI kit 流れ確認する
Note on I10: Lenovo: user login page user signup page
Note on J10: Lenovo: doctors page about us page
Note on K10: Lenovo: admin side 1. date page 2. doctor page
Note on L10: Lenovo: user design recheck
Note on M10: Lenovo admin side 1. add medicine page 2. edit medicine page design readjust for all pages
Note on N10: Lenovo: 1. about us edit page menu bar design change
Note on O10: Lenovo: screen design details
Note on P10: Lenovo: database discuss
Note on S10: Lenovo: discuss admin side design coding
Note on T10: Lenovo: admin side- 1. components 2. blog 3. edit current diseases
Note on U10: Lenovo: admin side_ 1.date 2.doctor catagories 3.doctor catagories(edit) 4.medicine 5.medicine (edit) 6. blood donation 7. contacct us
Note on D13: Lenovo: QR code system (admin) QR code system (patient)
Note on E13: Lenovo: patient history (admin) patient history (patient)
Note on F13: Lenovo: admin dashboard (display data) patient history (patient side) first testing
Note on G13: Lenovo: tesing meeting admin dashboard (today's patient list)
Note on D14: Lenovo: patient side -appointment page
Note on E14: Lenovo: patient history table appointment (patient side) boooking
Note on F14: Lenovo: admin pages alignments first testing
Note on G14: Lenovo: doctor search error resolve tesing meeting
Note on D15: Lenovo: admin side - del_flg modification
Note on F15: Lenovo: blood donation information first tesing
Note on G15: Lenovo: Inpatient button change about us info update change
Note on D16: Lenovo: admin side -forget password -logo
Note on E16: Lenovo: medicing page
Note on F16: Lenovo: medicine page information first tesing
Note on G16: Lenovo: tesing meeting

## 要件定義
要件定義 | プロジェクト名 |  | 作成日
|  |  | 更新日 | 2022-10-28 13:03
１.業務要件
１−１.システム化の背景
元気な、きんぜんな社会人生の生活になりるためその他の方法でようりつしたいの希望があるので
このシステムを開発します。
１−2.システム化の目的
このシステムは体の調しが良くないい各人のために病院に行きたい場合は予約することをう まくできたい
目的もあるいし、常備薬も用意するとき正常の方法で薬をえらべられるシステムを開発することです。
１−3.システム化後の業務フロー
後から,病人の側では医者任命するのため日常生活の仕事を迷惑しない出来るようになりましたいと思います。
つまり、急に病気の時にもげきてきしないで何がはじめにしなければならないのを役に立つことになります。病院の責任者側では病人についていろいろな経営(けいえい)をした時には複雑ではなく短く時間で出来るようになります。
| 2.機能要件 | 病院に行きたいの各人と病院の経営分野
2−１.システム全体像又は説明
名前として、システムがあるのが各人の健康について不満な、居心地が悪い感情についてその他の方法で治ることになります。

## 画面一覧
更新履歴 |  | VRCARER |  |  |  |  | 作成日 | 22/09/2022
[7 empty] | 更新日 | 2022-10-28 13:03
| NO | 画面名 |  |  |  | 内容説明
| 1 | 登録 |  |  |  | 新しいユーザーの情報を登録する
| 2 | パスワード編集 |  |  |  | パスワードを忘れたとき、ここに変更することができます
| 3 | ログイン |  |  |  | 名前とパスワードをいれてホームページにすずく
| 4 | 患者ホームページ |  |  |  | 病院と医者の情報を探す、予約できる、
| 5 | ユーザーセッティング |  |  |  | ユーザーの個人情報を確認できます
| 6 | ユーザーセッティング編集 |  |  |  | ユーザーの個人情報を編集できます
| 7 | 医者ペイジ |  |  |  | 欲しい専門医を選択のわできます, 日程を見て予約日と病院を選択する
| 8 | 予約ペイジ |  |  |  | 予約承認できるために必要な情報を申し込む
| 9 | 予約状況 |  |  |  | 申し込んた予約状況を確認できる,
| 10 | 病院住所 |  |  |  | 選択した病院の場所を地図に見せ付けます、選択した病院の情報を見せ付けます
| 11 | 医療情報ブログ |  |  |  | 応急処置、献血 について記事を読むことができます
| 12 | 緊急時代 |  |  |  | 緊急時代に必要な治療情報を探す、読むことができます
| 13 | 献血 |  |  |  | 献血センターの場所と連絡番号、献血の知識を読むことができます
| 14 | ウェブサイト案内 |  |  |  | このウェブサイトのプライバシーポリシーを説明しました
| 1 | 管理ログイン |  |  |  | 名前とパスワードをいれてホームページにすずく
| 2 | パスワード編集 |  |  |  | パスワードを忘れたとき、ここに変更することができます
| 3 | 管理ホームページ
| 4 | 病院住所 （編集） |  |  |  | 病院住所と連絡情報を見る編集することができます
| 5 | 予約ペイジ |  |  |  | 予約を承認する、断ることができます
| 6 | 患者病歴
| 7 | 患者病歴（加える）
| 8 | 入院患者 |  |  |  | 入院している患者の情報を見せます
| 9 | 入院患者 （加える） |  |  |  | 新しい入院している患者の情報を追加できます
| 10 | 入院患者（編集） |  |  |  | いま入院している患者の情報を編集できます
| 11 | デート |  |  |  | 医者の日程に予約した患者データを見て管理することができます
| 12 | 医者カテゴリ |  |  |  | 病院の医者のリストを見る、新しい医者情報を加えることができます。
| 13 | 医者カテゴリ（編集） |  |  |  | 病院の医者のリストを編集できます。
| 14 | 薬（加える） |  |  |  | 体の必要な薬の情報を見る、加えることができます
| 15 | 薬情報（編集） |  |  |  | 体の必要な薬の情報を編集できます。
| 16 | ブログ |  |  |  | ブログの題名と近、最近はやっている病気情報を見る、見ることができます
| 17 | ブログ（加える） |  |  |  | 最近はやっている病気情報を見る、編集ることができます
| 18 | 緊急時代（加える） |  |  |  | 緊急時代に必要な治療情報について加えることができます
| 19 | 緊急時代（編集） |  |  |  | 緊急時代に必要な治療情報について編集ることができます
| 20 | 献血（編集） |  |  |  | 献血センターの場所と連絡番号、献血の知識を加えることができます
| 21 | 連絡できる情報（編集） |  |  |  | このウェブサイトについてアドバイスする連絡情報を編集することができます
| 22 | クローセルのイメージチェンジ |  |  |  | クローセルの写真を変わることができます
| 23 | ウェブサイト案内（編集） |  |  |  | このウェブサイトのプライバシーポリシーを編集することができます
|  |  | 緊急時代（編集） | 緊急時代（編集） | 緊急時代（編集）

## 機能一覧
更新履歴 |  | プロジェクト名 |  | 作成日 | 2022-09-28
更新日
| NO | 機能名 | 内容説明 | ユーザ | 管理
| 1 | レジスター | ユーザを確認する,基本的に必要なデータをまとめることです | ●
| 2 | ログイン | ユーザまたは管理を確認することです | ● | ●
| 3 | 患者面 | アカウントがあるの方だたら自分の側面を見られます、かわることも できます | ●
| 4 | 医者助数詞 | 色々な専門家医者を見られます。予約のため何時にとこのある病院名も見られますまたはしらべられます。管理側ではこの助数詞を経営することもできます。 | ● | ●
| 5 | 予約フォーム | 病院で医者に会いたいのに病院を申し込むことです | ●
| 6 | 患者一覧整理 | 患者の申し込むデータをしょうにんずられるまたはキャンセルすること |  | ●
| 7 | 日助数詞 | その日のある患者一覧とか医者一覧とか見られます |  | ●
| 8 | 患者歴史 | 病気名、医者から案内すること、薬と飲んだ方法、つきの任命なとを 管理なら管制します。 | ● | ●
| 9 | 入院する方の一覧 | 入院にはじめの日、患者側面、病気のようすなとを管制こともできます |  | ●
| 10 | 薬の承認 | 薬の効能についておすすめることです。ようそ値段もおすすめます | ● | ●
| 11 | 最近流行する病気の放送 | 伝染病の理由と広がるの方法をお知らせられます | ● | ●
| 12 | 日所の場合 | 色々な応急手当ての方法をおすすめますした | ● | ●
| 13 | 病院検索 | この町にある病院の場所をしらべられます。病院の情報もみられます | ●
14

## フロント流れ
画面流れ |  | プロジェクト名 |  |  |  | 作成日
[6 empty] | 更新日 | 2022-10-28 13:03
フロント画面流れ
| Screen Flow Chart Name | User Panel |  | 画面流れ図名前― | ユーザ
T_CU_Coin
|  | customer_id | Customer ID
|  | coin | Coin Balance
|  | approve_By | Approve By

## 管理画面流れ
画面流れ |  | プロジェクト名 |  |  |  | 作成日
[6 empty] | 更新日 | 2022-10-28 13:03
管理画面流れ
| Screen Flow Chart Name - | Admin Panel |  | 画面流れ図名前ー | アドミン
T_CU_Coin
|  | customer_id | Customer ID
|  | coin | Coin Balance
|  | approve_By | Approve By

## 画面デザイン
画面デザイン | プロジェクト名 | [8 empty] | 作成日
[10 empty] | 更新日 | 2022-09-22
User
Screen Name ： |  | Login |  | Screen Name ： |  | Sign-Up |  | Screen Name ： |  | Forget Password
Screen Name ： |  | Home Screen |  | Screen Name ： |  | Hospital Location |  | Screen Name ： |  | Doctors Page
Screen Name ： |  | Appointment Form | Screen Name ： |  | Booking Status and History
Screen Name ： |  | Home Screen |  | Screen Name ： |  | Hospital Location |  | Screen Name ： |  | Doctors Page
Screen Name ： |  | Home Screen |  | Screen Name ： |  | User Profile Setting |  | Screen Name ： |  | User Profile Edit
Admin
|  |  |  | Screen Name ： |  | Login
| Screen Name ： |  | Admin Dashboard |  |  |  | Screen Name ： |  | Hospital Location
| Screen Name ： |  | Patient History |  |  |  | Screen Name ： |  | Add Patient History
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login |  |  |  | Screen Name ： |  | Forget Password
| Screen Name ： |  | Login

## DB 設計
DB設計 |  | プロジェクト名 | [8 empty] | 作成日
[11 empty] | 更新日 | 2022-09-22
| DB 名 ： |  | MEDPLATFORM
| Table Name ： |  | User Register
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | register_id | Register ID | ● | ● | ● | INT | 11
| 2 | email_address | email address |  |  | ● | VARCHAR | 128 |  | unique
| 3 | password | account password |  |  | ● | VARCHAR | 128
| 4 | del_flg | Delete flag
| 5 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 6 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Admin data
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Admin_ID | admin id | ● | ● | ● | INT | 11
| 2 | Admin_name | admin name |  |  | ● | VARCHAR | 128
| 3 | password | admin password |  |  | ● | VARCHAR | 20
| 4 | admin status | admin role |  |  |  | INT | 2 |  | 1 = main admin 2= booking admin 3 = record admin
| 5 | del_flg | Delete flag
| 6 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 7 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | User Profile
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Register_id | Register ID | ● | ● | ● | INT | 11
| 2 | Profile_picture | user profile picture |  |  |  | VARCHAR | 256
| 4 | Username | username |  |  | ● | VARCHAR | 128
| 5 | age | user age |  |  | ● | INT | 3
| 6 | Contact | phone number |  |  | ● | VARCHAR | 15
| 7 | Address | address |  |  |  | VARCHAR | 256
| 9 | del_flg | Delete flag
| 10 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 11 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Doctor
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Doctor_id | doctor id | ● | ● | ● | INT | 11
| 2 | Doctor_name | doctor name |  |  | ● | VARCHAR | 128
| 3 | Speciality | doctor speciality |  |  | ● | VARCHAR | 128
| 4 | age | age |  |  | ● | INT | 3
| 5 | gender | doctor gender |  |  | ● | INT | 3
| 6 | contact | contact |  |  | ● | INT | 15
| 7 | Hospital name | hospital name |  |  |  | VARCHAR | 128
| 8 | profile_photo | profile_photo |  |  |  | VARCHAR | 256
| 9 | date_id | date_id |  |  | ● | INT | 11
| 10 | del_flg | Delete flag
| 11 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 12 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Date
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Date_id | date id | ● | ● | ● | INT | 11
| 2 | Doctor_id | doctor id |  |  | ● | INT | 11
| 3 | Date | date |  |  | ● | VARCHAR | 10
| 4 | time | time |  |  | ● | VARCHAR | 5 |  | 0:00
| 5 | hospital | hospital name |  |  |  | VARCHAR | 128
| 6 | del_flg | Delete flag |  |  |  | INT
| 7 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | booking
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | booking_id | booking_id | ● | ● | ● | INT | 11
| 2 | register_id | register id |  |  | ● | INT | 11
| 3 | email address | email address |  |  | ● | VARCHAR | 128
| 4 | name | name |  |  | ● | VARCHAR | 128
| 5 | age | age |  |  | ● | INT | 3
| 6 | gender | gender |  |  | ● | INT | 3
| 7 | contact | contact |  |  | ● | INT | 15
| 8 | address | address |  |  |  | VARCHAR | 258
| 9 | booking_time | booking_time |  |  | ● | VARCHAR | 5 |  | 0:00
| 10 | date_id | date_id |  |  | ● | INT | 11
| 11 | doctor_id | doctor_id |  |  | ● | INT | 11
| 12 | booking_status | booking_status |  |  | ● | INT | 11 |  | 0 = pending 1 = approved 2 = rejected
| 13 | del_flg | Delete flag |  |  |  | INT
| 14 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 15 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | approve_booking
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | booking_id | booking_id | ● | ● | ● | INT | 11
| 2 | register_id | register id |  |  | ● | INT | 11
| 3 | email address | email address |  |  | ● | VARCHAR | 128
| 4 | name | name |  |  | ● | VARCHAR | 128
| 5 | age | age |  |  | ● | INT | 3
| 6 | gender | gender |  |  | ● | INT | 3 |  | 0 = MALE 1 = FEMALE 3 = PREFER NOT TO TELL
| 7 | contact | contact |  |  | ● | INT | 15
| 8 | address | address |  |  |  | VARCHAR | 258
| 9 | booking_time | booking_time |  |  | ● | VARCHAR | 5 |  | 0:00
| 10 | date_id | date_id |  |  | ● | INT | 11
| 11 | hospital_name | hospital_name |  |  | ● | VARCHAR | 128
| 12 | doctor_id | doctor_id |  |  | ● | INT | 11
| 13 | booking_status | booking_status |  |  | ● | INT | 11 |  | 1 = approved
| 14 | del_flg | Delete flag |  |  |  | INT
| 15 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 16 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | reject_booking
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | booking_id | booking_id | ● | ● | ● | INT | 11
| 2 | register_id | register id |  |  | ● | INT | 11
| 3 | email address | email address |  |  | ● | VARCHAR | 128
| 4 | name | name |  |  | ● | VARCHAR | 128
| 5 | age | age |  |  | ● | INT | 3
| 6 | gender | gender |  |  | ● | INT | 3
| 7 | contact | contact |  |  | ● | INT | 15
| 8 | address | address |  |  |  | VARCHAR | 258
| 9 | booking_time | booking_time |  |  | ● | VARCHAR | 5 |  | 0:00
| 10 | date_id | date_id |  |  | ● | INT | 11
| 11 | doctor_id | doctor_id |  |  | ● | INT | 11
| 12 | booking_status | booking_status |  |  | ● | INT | 11 |  | 0 = pending 1 = approved 2 = rejected
| 13 | del_flg | Delete flag |  |  |  | INT
| 14 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 15 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | patient_history
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | patient_id | patient_id | ● | ● | ● | INT | 11
| 2 | booking_id | booking id |  |  | ● | INT | 11
| 3 | register_id | register_id |  |  | ● | INT | 11
| 4 | doctor_id | doctor_id |  |  |  | INT | 11
| 5 | date_id | date |  |  | ● | VARCHAR | 11
| 6 | patient_name | patient_name |  |  | ● | VARCHAR | 128
| 7 | disease | disease |  |  | ● | VARCHAR | 128
| 8 | medicine | medicine |  |  | ● | VARCHAR | 128
| 9 | next_appointment_date | next_appointment_date |  |  |  | VARCHAR | 10
| 10 | next_appointment_time | next_appointment_time |  |  |  | VARCHAR | 5
| 11 | hospital_name | hospital_name |  |  | ● | VARCHAR | 128
| 12 | del_flg | Delete flag
| 13 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 14 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | inpatient_history
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | inpatient_id | inpatient_id | ● | ● | ● | INT | 11
| 2 | inpatient_name | inpatient name |  |  | ● | VARCHAR | 128
| 3 | inpatient_age | inpatient age |  |  | ● | INT | 3
| 4 | address | inpatient address |  |  | ● | VARCHAR | 256
| 5 | patient_status | inpatient status |  |  | ● | VARCHAR | 128 |  | Normal ICU HCU
| 6 | disease | disease |  |  | ● | VARCHAR | 256
| 7 | hospitalized_date | hospitalized date |  |  | ● | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | room number | room number |  |  | ● | INT | 11
| 9 | del_flg | Delete flag
| 10 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 11 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | hospital location
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | hospital_id | hospital_id | ● | ● | ● | INT | 11
| 2 | hospital_name | hospital name |  |  | ● | VARCHAR | 128
| 3 | address | hospital address |  |  | ● | VARCHAR | 256
| 4 | email | hospital mail |  |  | ● | VARCHAR | 128
| 5 | contact | hospital contact |  |  | ● | VARCHAR | 15
| 6 | google_map_image | google map image |  |  | ● | VARCHAR | 256
| 7 | del_flg | Delete flag
| 8 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 9 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Current Diseases
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Disease_id | disease ID | ● | ● | ● | INT | 11
| 2 | header | disease header |  |  | ● | VARCHAR | 128
| 3 | paragraph | disease paragraph |  |  | ● | VARCHAR | 512
| 4 | image | disease image |  |  | ● | VARCHAR | 256
| 5 | del_flg | Delete flag
| 6 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 7 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | blood_donation
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Center_id | center ID | ● | ● | ● | INT | 11
| 2 | center_name | center name |  |  | ● | VARCHAR | 128
| 3 | center_address | center address |  |  | ● | VARCHAR | 256
| 4 | center_contact | center contact |  |  | ● | VARCHAR | 15
| 5 | center_email | center email |  |  |  | VARCHAR | 128
| 6 | del_flg | Delete flag
| 7 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Blog
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | Blog_id | blog id | ● | ● | ● | INT | 11
| 2 | tab_1_text | text for tab1 |  |  |  | VARCHAR | 128
| 3 | tab_1_image | img for tab1 |  |  | ● | VARCHAR | 256
| 4 | tab_2_text | text for tab2 |  |  |  | VARCHAR | 128
| 5 | tab_2_image | img for tab2 |  |  | ● | VARCHAR | 256
| 6 | del_flg | Delete flag
| 7 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
9
| Table Name ： |  | Medicine (home page)
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | medicine_ID | Medicine id | ● | ● | ● | INT | 11
| 2 | medicine_name | medicine name |  |  | ● | VARCHAR | 128
| 3 | medicine_description | medicine description |  |  | ● | VARCHAR | 512
| 4 | medicine_advantage | medicine advantage |  |  | ● | VARCHAR | 256
| 5 | medicine_image | medicine image |  |  | ● | VARCHAR | 256
| 6 | del_flg | Delete flag
| 7 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Emergency_page_header
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | header_id | header ID | ● | ● | ● | INT | 11
| 2 | header | article header |  |  | ● | VARCHAR | 128
| 3 | text | article text |  |  | ● | VARCHAR | 512
| 4 | del_flg | Delete flag
| 5 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 6 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | First Aid
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | article_id | first aid ID | ● | ● | ● | INT | 11
| 2 | article_header | article header |  |  | ● | VARCHAR | 128
| 3 | article_text | article text |  |  | ● | VARCHAR | 512
| 4 | article_image | article image |  |  |  | VARCHAR | 256
| 5 | del_flg | Delete flag
| 6 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 7 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Caroussel
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | caroussel_id | caroussel id | ● | ● | ● | INT | 11
| 2 | caroussel_image | caroussel_image1 |  |  | ● | VARCHAR | 256
| 3 | caroussel_image2 | caroussel_image2 |  |  | ● | VARCHAR | 256
| 4 | caroussel_image3 | caroussel_image3 |  |  | ● | VARCHAR | 256
| 5 | caroussel_image4 | caroussel_image4 | - | - |  | VARCHAR | 256
| 6 | del_flg | Delete flag
| 7 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 8 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | About Us
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | info_id | about us id | ● | ● | ● | INT | 11
| 2 | info_1 | info 1 |  |  | ● | VARCHAR | 256
| 3 | image_1 | image 1 |  |  |  | VARCHAR | 256
| 4 | header |  |  |  | ● | VARCHAR | 128
| 5 | paragraph | info 2 |  |  | ● | VARCHAR | 256
| 6 | image_2 | image 2 |  |  |  | VARCHAR | 256
| 7 | del_flg | Delete flag
| 8 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 9 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Policy
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | policy_id | policy_id | ● | ● | ● | INT | 11
| 2 | policy_text | policy_text |  |  | ● | VARCHAR | 512
| 3 | policy_image | policy_image |  |  |  | VARCHAR | 256
| 4 | del_flg | Delete flag
| 5 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 6 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | next_apointment
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | next_boking_id | next_boking_id | ● | ● | ● | INT | 11
| 2 | patient_id | patient_id |  |  | ● | INT | 11
| 3 | booking_id | booking_id |  |  | ● | INT | 11
| 4 | date | date |  |  | ● | VARCHAR | 10
| 5 | time | time |  |  | ● | VARCHAR | 5
| 7 | del_flg | Delete flag
| 8 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 9 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| Table Name ： |  | Contact Us
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | new_info_id | new_info_id | ● | ● | ● | INT | 11
| 2 | new_contact | new_contact |  |  | ● | INT | 15
| 3 | new_address | new_address |  |  | ● | VARCHAR | 256
|  | new_paragraph | new_paragraph |  |  |  | VARCHAR | 256
| 4 | icon1 | icon1 |  |  |  | VARCHAR | 256
| 5 | icon2 | icon2 |  |  |  | VARCHAR | 256
| 6 | icon3 | icon3 |  |  |  | VARCHAR | 256
| 7 | del_flg | Delete flag
| 8 | created_date | Date this table was created |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD
| 9 | updated_date | Date this table was updated |  |  |  | VARCHAR | 10 |  | YYYY/MM/DD

## DB 図
DB設計 | プロジェクト名 | 作成日
|  | 更新日 | 2022-09-22

## ユーザーマニュアル
ユーザー マニュアル | プロジェクト名 | 作成日
|  | 更新日 | 2022-09-22

## メールフォーマット
〜〜〜〜様 お疲れ様です。 （YYYY /MM /DD）の進捗を報告致します。 担当者 タスク 完了％ ーーー ーーー ーーー Linn Ko ログイン画面 １０％ 問題 ＝＝＝ DBに繋がらない。 解決方法 ＝＝＝＝ 再起動してまた起動しました。 次のタスク ＝＝＝＝＝ 担当者 タスク 予定完了％ ーーー ーーー ーーーーー Linn Ko ログイン画面 ２０％ 以上です。 宜しくお願い致します。 グループ名 担当者